## Sheet1
Section | Sub-Section | Task/Information | Start Date | End Date | Notes/Resources
Project Overview | - | Django To-Do List Application | 15/10/2023 | 15/12/2023 | Develop a simple and intuitive task management tool allowing users to create, manage, and organize tasks.
Key Stakeholders | - | Product Owner: [Name] | - | - | -
Key Stakeholders | - | Scrum Master: [Name] | - | - | -
Key Stakeholders | - | Development Team: [List of developers] | - | - | -
Sprints and Milestones | Sprint 1: Design and Setup | Design mockups for the application. | 15/10/2023 | 29/10/2023 | -
Sprints and Milestones | Sprint 1: Design and Setup | Set up the Django development environment. | 15/10/2023 | 29/10/2023 | -
Sprints and Milestones | Sprint 1: Design and Setup | Set up version control (e.g., Git). | 15/10/2023 | 29/10/2023 | -
Sprints and Milestones | Sprint 2: Core Features Development | Implement the 'Create a new task' feature. | 30/10/2023 | 19/11/2023 | -
Sprints and Milestones | Sprint 2: Core Features Development | Implement the 'Edit an existing task' feature. | 30/10/2023 | 19/11/2023 | -
Sprints and Milestones | Sprint 2: Core Features Development | Implement the 'Delete a task' feature. | 30/10/2023 | 19/11/2023 | -
Sprints and Milestones | Sprint 3: Advanced Features Development | Implement 'Assign a task to a category or project' feature. | 20/11/2023 | 2023-10-12 | -
Sprints and Milestones | Sprint 3: Advanced Features Development | Implement 'View tasks by category or project' feature. | 20/11/2023 | 2023-10-12 | -
Sprints and Milestones | Sprint 3: Advanced Features Development | Implement 'Set due dates for tasks' feature. | 20/11/2023 | 2023-10-12 | -
Sprints and Milestones | Sprint 4: Additional Features and Testing | Implement 'Mark tasks as complete' feature. | 2023-11-12 | 24/12/2023 | -
Sprints and Milestones | Sprint 4: Additional Features and Testing | Start initial testing and debugging. | 2023-11-12 | 24/12/2023 | -
Sprints and Milestones | Sprint 5: Testing, Debugging, and Documentation | Complete thorough testing. | 25/12/2023 | 2024-08-01 | -
Sprints and Milestones | Sprint 5: Testing, Debugging, and Documentation | Debug identified issues. | 25/12/2023 | 2024-08-01 | -
Sprints and Milestones | Sprint 5: Testing, Debugging, and Documentation | Finalize documentation and user manuals. | 25/12/2023 | 2024-08-01 | -
Sprints and Milestones | Sprint 6: Deployment and Feedback | Deploy the Django application. | 2024-09-01 | 16/01/2024 | -
Sprints and Milestones | Sprint 6: Deployment and Feedback | Collect user feedback. | 2024-09-01 | 16/01/2024 | -
Sprints and Milestones | Sprint 6: Deployment and Feedback | Make necessary quick fixes based on feedback. | 2024-09-01 | 16/01/2024 | -
Dependencies | - | Django Framework | - | - | -
Dependencies | - | Database (e.g., PostgreSQL, SQLite) | - | - | -
Dependencies | - | Front-end libraries (e.g., Bootstrap) | - | - | -
Dependencies | - | Version Control (e.g., Git) | - | - | -
Risks and Mitigation | Scope creep - Introduction of features not initially agreed upon. | - | - | Any new features will be considered for future iterations.
Risks and Mitigation | Technical challenges with Django. | - | - | Provide additional training or resources as needed. Consider consultation with Django experts.
Communication | - | Daily Scrum Meetings: 15 minutes, every day. | - | - | -
Communication | - | Sprint Review: End of each sprint. | - | - | -
Communication | - | Sprint Retrospective: After every sprint review. | - | - | -
Communication | - | Sprint Planning: Beginning of each sprint. | - | - | -
Tools | - | Project Management: Jira, Trello, or Asana | - | - | -
Tools | - | Version Control: Git (with GitHub, GitLab, or Bitbucket) | - | - | -
Tools | - | Communication: Slack, Teams, or Discord | - | - | -
Tools | - | Documentation: Confluence or Google Docs | - | - | -